| District Strategic Plan 2016-2017 Action Plans Owner(s): Pam Moore, Rita Vasquez, Dywayne Hinds, Shana Rafalski, Sherry Aemisegger |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Goal / (2 ): |  | Ensure curriculum, instruction, and assessment is designed and delivered with a focus on content rigor, student engagement, and continuous improvement of academic achievement. |  |  |  |  |  |  |  |  |
| Action Plan: (1 ) | Increase the percentage of aligned standards-based instruction and tasks, rigor, and student-centered learning as measured by ISM visit data collection. |  |  |  |  |  |  |  |  |  |
| Steps |  |  | Schedule |  | Deliverables | Measures | Current Actuals | Targets |  |  |
|  |  |  | Start | Finish |  |  |  | 2016 | 2017 |  |
| - Define excellent instruction (after review of research) |  |  | 3/16 | 7/16 | Communication including definitions of excellent instruction | Evidence of shared understanding and demonstration of excellent instruction | On-going | 10% | 100% |  |
| - Professional Development on Rigor |  |  | 10/16 | 7/17 | Development and delivery of training | Number of teachers attending PD | On-going |  | 100% |  |
| - Develop rubrics for Student Work – process for review of student work for standards-based planning/adjustments |  |  | 6/16 | 7/17 | Development and delivery of training to use the rubrics | Evidence of use of rubrics (classroom walkthroughs) | On-going |  | 100% |  |
| - Redesign Instructional Support Model for adjustments to priorities for 16-17 |  |  | 5/16 | 8/16 | ISM data collect ion sheet and online documents | Debrief documents and results from forms | completed |  |  |  |
| - School walks during Area Meetings (part of Leadership Development Plans) |  |  | 9/16 | 7/17 | Communication using the Consultancy Protocol | Evidence of shared understanding and demonstration of excellent instruction (also reflected in School Leader Appraisals) | On-going |  |  |  |
| - Leadership Professional Development |  |  | 6/16 | 7/17 | Development and delivery of trainings | Area and Leadership meetings - documents | On-going |  | 100% |  |
| - Focused Content Area Professional Development |  |  | 6/16 | 7/17 | Development and delivery of training | Number of teachers attending PD | On-going |  | 100% |  |
| - Piloting MAP assessments in K-5 schools (targeted and control groups) |  |  | 3/16 | 7/16 | Professional Development | Data analysis of results | New |  |  |  |
| - Create instructional materials committees K-12 for ELA and Math supplemental materials – especially effective with students of color. |  |  | 3/17 | On-going | Review minutes/actions from each level committees | Curriculum guides to include additional resources to support the learning for ALL students. | On-going |  |  |  |
| - Create summer PD calendar, 2017. |  |  | 1/17 | 5/12 | Comprehensive list for summer, 2017 | Plan delivered during the April, 2017 Leadership meeting to allow for early registrations. |  |  |  |  |
| Comments: |  |  |  |  |  |  |  |  |  |  |