| District Strategic Plan 2016-2017 Action Plans Owner(s): Pam Moore, Rita Vasquez, Dywayne Hinds, Shana Rafalski |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Goal / ( 3): |  | Develop and sustain a healthy, respectful, caring, safe learning environment for students, faculty, and community resulting in individual employee learning, student achievement and overall school improvement. |  |  |  |  |  |  |  |  |
| Action Plan: (3 ) | Develop required qualifications and monitor the role, and effectiveness of all academic coaches by the increase in achievement levels of subject areas of assignment. |  |  |  |  |  |  |  |  |  |
| Steps |  |  | Schedule |  | Deliverables | Measures | Current Actuals | Targets |  |  |
|  |  |  | Start | Finish |  |  |  | 2016 | 2017 |  |
| - Review the “Pinellas Coaching Vision” document created in partnership with TNTP and district/school-based staff. |  |  | 7/16 | 7/16 | Meeting held to review document | Meeting held. | completed |  |  |  |
| - Include information in the “handbook” designed to communicate what good instruction looks like – what students are doing, what teachers are doing, what coaches are doing, and what leaders are doing. |  |  | Initiated in 8/16 | 9/16 | Document to share with school leaders/teachers | Document completed |  |  |  |  |
| - Develop Coaching Academy – 2016-2017 |  |  | 7/16 | 8/16 | Academies held during the second week of August, 2016 | Professional development completed | Completed |  |  |  |
| - Fill all vacancies before school begins on August 10th |  |  | 5/16 | 7/16 | Filled vacancies | 100% staffed | completed |  |  |  |
| - Set performance targets for coaches by content area in terms of monitoring of standards-based instruction, rigorous lessons, differentiated instruction. |  |  | 8/16 | 8/16 | Priorities used in PD at August trainings (and reinforced across the school year) | 100% of teachers delivering standards-based instruction; 100% of teachers planning rigorous tasks towards mastery of standards; 100% of teachers able to differentiate instruction for all learners. Data collected across the year during ISM visits. |  |  | 100% of teachers observed |  |
| - Work with AAR and PD departments to align data/appraisal data to determine if achievement has increased as a result of coaching opportunities. |  |  | 10/16 | On-going | Processes established | Appraisal data/performance data |  |  |  |  |
| - Recommend changes in coaching model for 17-18 |  |  | 4/17 | 5/17 | Recommendations for staffing model | Alignment to budget and effectiveness models. |  |  |  |  |
| Comments: |  |  |  |  |  |  |  |  |  |  |