| District Strategic Plan 2015-2016 Action Plans Owner(s) Pam Moore, supported by Rita Vasquez, Dywayne Hinds, Sandy Downes, and ESE Executive Director |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Goal / (2 ): |  | Ensure curriculum, instruction, and assessment is designed and delivered with a focus on content rigor, student engagement, and continuous improvement of academic achievement. |  |  |  |  |  |  |  |  |
| Action Plan: ( 1) | Ensure that all content area professional development is aligned to the Florida Standards or Next Generation Sunshine State Standards. |  |  |  |  |  |  |  |  |  |
| Steps |  |  | Schedule |  | Deliverables | Measures | Current Actuals | Targets |  |  |
|  |  |  | Start | Finish |  |  |  | 2015 | 2016 |  |
| - Create Master Plan for Summer, 2015 aligned to Florida Standards |  |  | 1/2015 | 2/2015 | Full Summer PD Plan delivered to Principals at the March, 2015 Leadership meeting | Plan delivered Number of teachers who participated in trainings |  | Summer of 2015: Teachers took at least 1 course | Summer of 2016: Teachers took at least 1 course |  |
| - Create Master Plan for “Just in Time and content-specific before/after ours trainings across all levels and content areas (with FS or NGSSS standards embedded) |  |  | 7/2015 | 7/2015 | Calendars with professional development offerings – advertised through schools | Number of teachers who participated in trainings |  |  |  |  |
| - Align budget requests to proposed professional development opportunities. |  |  | 2/2015 for 2016 | 2/2016 for 2017 | Budget alignment to match calendared options |  |  |  |  |  |
| - Create Master Plan for Summer, 2016 (with FL/NGSSS embedded) |  |  | 1/2016 | 3/2016 | Full Summer PD Plan delivered to Principals at the March, 2016 Leadership meeting | Plan delivered Number of teachers who participated in trainings |  |  |  |  |
| Comments: Planning for summer, 2016 will begin in January, 2016 and will continue to be placed on all Leadership Team agendas for Teaching and Learning staff meetings. We will strive to decrease the number of trainings requiring TDEs. |  |  |  |  |  |  |  |  |  |  |