| District Strategic Plan 2014-2015 Action Plans Owner(s) Pam Moore, Rita Vasquez, Dywayne Hinds, Sandy Downes |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Goal / (2 ): |  | Ensure curriculum, instruction, and assessment is designed and delivered with a focus on continuous improvement of student engagement and academic achievement. |  |  |  |  |  |  |  |  |
| Action Plan: (2 ) | Increase the quality of engaging reading, writing, math, and science instruction to prepare minority and economically disadvantaged students at all levels for rigorous coursework and multiple program opportunities by using proven strategies that lead to increased student learning. |  |  |  |  |  |  |  |  |  |
| Steps |  |  | Schedule |  | Deliverables | Measures | Current Actuals | Targets |  |  |
|  |  |  | Start | Finish |  |  |  | 2014 | 2015 |  |
| - Work with school teams in preparing goal statements regarding minority students to be included in their school improvement plans. |  |  | Summer, 2014 | Fall, 2014 | Individual School Improvement Plan achievement goals in reading, writing, math, and science | SIP Evaluation Template with feedback – on-line tool | All school plans were reviewed with feedback using template. | Met the target in summer, 2014 | Will continue process during summer, 2015 |  |
| - Review district data of subgroups to determine trends and/or gaps. |  |  | Summer, 2014 | Fall, 2014 | At Risk Data Reports – AAR/Reports Manager; Performance Matters | FCAT Results for 13-14 |  |  | Completed in Fall, 2014 |  |
| - Provide schools with scheduling recommendations to ensure minority students are enrolled in appropriate coursework using current academic data and recommendations. |  |  | 8/14 | 9/14 | Address through agendas at both principal and assistant principal meetings in fall, 2014. | Schedules reviewed by school. |  |  | Completed, in Fall, 2014 |  |
| - Review of existing programs, and applications in current use for ELL and AA students. |  |  | 9/14 | On-going | Examination of curricular materials to supplement core instruction. | Common assessment data review by cycle. | Data reviews conducted after each cycle using Perf. Matters Executive Reports |  | on-going |  |
| - Examination of the Lowest performing elementary sites (L300) and the five lowest performing elementary sites to build full scale plan – Scale Up |  |  | 9/14 | On-going implementation checks | Scale Up Plan and Implementation Evaluation Plan | Measures determined within the implementation Plan | 10/14 |  | Scale-Up Evaluation Plan, 1/15 |  |
| - Participation in “Bridging the Gap” as goal managers – detailing the plans impacting the achievement of minority students: Goals 1, 2,3, and 5 are managed through Teaching and Learning |  |  | 8/14 | 7/15 | Bridging the Gap Action Plans completed (11/14) Goal Managers: Goal 1, Rita Vasquez; Goal 2, Pam Moore; Goal 3, Judy Vigue; and Goal 5, Lisa Grant | FCAT Common Assessment PERT ACT/SAT College Readiness AP Participation rates PSAT ReadiStep |  |  | Plans completed by 11/14 |  |
| - Follow up with guidance counselors, APCs, and principals to monitor course placements and encourage AVID courses, and testing opportunities. This step includes master scheduling training offered throughout the year and using the reading and math sorters in MS and HS> |  |  | 9/14 | On-going | Meeting agendas | Master Schedules |  |  | On-going |  |
| Comments: Scale Up – new for 2014-2015 to support/assist the five lowest-performing elementary sites. |  |  |  |  |  |  |  |  |  |  |