| District Strategic Plan 2015-2016 Action Plans Owner(s) Pam Moore, Rita Vasquez, Dywayne Hinds, Sandy Downes |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Goal / (2 ): |  | Ensure Curriculum, instruction, and assessment is designed and delivered with a focus on continuous improvement of student engagement and academic achievement. |  |  |  |  |  |  |  |  |
| Action Plan: (3) | Monitor curriculum implementation through the use of observation rubrics to gather data at both the school and district level t determine effectiveness of implementation and inform professional development plans. |  |  |  |  |  |  |  |  |  |
| Steps |  |  | Schedule |  | Deliverables | Measures | Current Actuals | Targets |  |  |
|  |  |  | Start | Finish |  |  |  | 2014 | 2015 |  |
| - Revise Instructional Support Model observation tools (including rubrics and feedback forms) |  |  | 6/14 | 8/14 | Revised ISM handbooks including all data collection tools. | Share with principals at first Leadership meeting in August. |  |  | Model revisions completed in 8/14; ISM visits, on-going |  |
| - Complete ISM visit schedule and coordinate with Area Superintendents |  |  | 8/14 | 8/14 | Calendar completion – (often requires adjustments throughout the year) | Publish for Area Superintendents, Executive Directors, Principals, Content Specialists |  |  | Done, 9/14 |  |
| - Review ISM data at weekly “A Team Meetings” with Deputy Superintendent, Area Sups |  |  | 8/14 | On-going weekly | Summaries discussed weekly; share electronically. | A Team members: Corbett, Wright, Poth, Kennedy, Hires, Moore, Vasquez, Hinds, Downes, Grant, Matway, Sicilian |  |  | On-going |  |
| - Using ISM visits reports, schedule “just in time” trainings for specific schools |  |  | 9/14 | On-going | Changes to PD calendars Schedules for follow up trainings | Monitoring reports by content specialists as to who attended |  |  | On-going |  |
| - Plan summer retreat for T & L, PD, and Area Sups to refine process for 15-16 |  |  | 4/15 | 7/15 | Modifications to ISM process | Retreat held. |  |  | Completed during A Team meetings |  |
| Comments: |  |  |  |  |  |  |  |  |  |  |