| District Strategic Plan 2015-2016 Action Plan Owner(s) : Pam Moore, Sandy Downes, Dywayne Hinds, Rita Vasquez |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Goal / (2 ): |  | Ensure curriculum, instruction, and assessment is designed and delivered with a focus on content rigor, student engagement, and continuous improvement of academic achievement. |  |  |  |  |  |  |  |  |
| Action Plan: (10) | Utilize comprehensive curriculum guides including appropriate formative and summative assessments in all subject areas and support teachers in using the curriculum guides through professional development. |  |  |  |  |  |  |  |  |  |
| Steps |  |  | Schedule |  | Deliverables | Measures | Current Actuals | Targets |  |  |
|  |  |  | Start | Finish |  |  |  | 2015 | 2016 |  |
| - Develop/revise Curriculum Maps/Guides annually including recommendations for formative assessments. |  |  | 2/2016 | 5/2016 | Curriculum Maps/Guides ready for use during Summer, 2016 professional development. | Guides will be printed/posted and available to teachers for summer, 2016 trainings. | . On-going | . |  |  |
| - Development/implementation of PCS common assessments by grade level and subject area. |  |  | Summer, 2015 | On-going | Assessments ready for cycles 1, 2, and 3 | All assessments will be ready for use by teachers/schools as scheduled |  |  |  |  |
| - Development of Professional Development schedules and modules for trainings (Summer, 2015 and during the school year) using curriculum maps/guides |  |  | Summer, 2015 | On-going across the school year | Content specialists send monthly communications to teachers and administrators to advertise opportunities. | Number of teachers attending PD opportunities. |  | Individual content areas tract participation levels | Individual content areas tract participation levels |  |
| - Development/implementation of Instructional Support Model (ISM) for school instructional reviews by district staff and Area Superintendents for ALL schools. |  |  | Scheduled by 8/2015 | Across school year | ISM reports posted for schools and A Team members to consistently review. | Data collection on the implementation of standards-based curriculum, use of goals/scales, and student engagement with curriculum |  | Data is live in tool to give us % observed in targeted areas. |  |  |
| - Share common assessment data with principals, assistant principals, and LLC cadres for further analysis at school and team/department levels. |  |  | 9/2015 | On-going | Data reports for administrators through Performance Matters – AAR providing assistance | Performance Matters data reports using with principals/teams during school visits. |  | Occurs during school visits |  |  |
| - Review data for targeted schools at A Team meetings weekly (schools discussed on rotating schedules) |  |  | 8/2015 | weekly | Use A Team folder created for all members to include SIP, SIP eval, SIP Ex Summary, ISM reports, Data/assessment results/progress monitoring | A Team minutes |  | Weekly |  |  |
| Comments: |  |  |  |  |  |  |  |  |  |  |