| District Strategic Plan 2015-2016 Action Plan Owner(s) Pam Moore, Lou Cerreta |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Goal / (3 ): |  | Develop and sustain a healthy, respectful, caring, safe learning environment for students, faculty, staff, and community resulting individual employee learning, student achievement and overall school improvement. |  |  |  |  |  |  |  |  |
| Action Plan: (6) | Provide professional development offerings based on prioritized needs identified through teacher appraisal data and deliberate practice processes evaluated by teacher survey results. |  |  |  |  |  |  |  |  |  |
| Steps |  |  | Schedule |  | Deliverables | Measures | Current Actuals | Targets |  |  |
|  |  |  | Start | Finish |  |  |  | 2015 | 2016 |  |
| - Transition to new platform for recording professional development opportunities (True North Logic) |  |  | 9/1/15 | 9/1/15 | All new components must be rewritten and resubmitted to new platform, and approved by PD Department. | Components written and in the system, available to teachers. | Transition to be completed by end of September. | . |  |  |
| - Gather information from True North Logic regarding the requests for professional development as indicated through Deliberate Practice Plans |  |  | 10/15 | 11/20/15 | Ability to obtain this information from the new system. | List of requests by the end of November |  |  |  |  |
| - Coordinate meeting of T & L and PD staff to evaluate the requests and adjust current PD opportunities |  |  | 12/15 | 12/15 | Meeting scheduled | Actions from meeting |  |  |  |  |
| - Content specialists and professional development staff build the master plan for second semester and summer, 2016 |  |  | 1/16 | 1/16 | Master plan developed | Components written, scheduled, and opened for participation. |  |  |  |  |
| - Refine evaluation of PD |  |  | 2/16 | 2/16 | PD Department will design the changes to determine quality and implementation as a results of PD participation | Evaluation redesign completed by end of February |  |  |  |  |
| - Share changes with Leadership |  |  | 3/16 | 3/16 | Meetings scheduled | Meetings held with specific instructions for principals to share with staff |  |  |  |  |
| - PD department to build communication plan around these changes. |  |  | 4/16 | 4/16 | Plan completed. | Plan shared by end of April. |  |  |  |  |
| Comments: |  |  |  |  |  |  |  |  |  |  |